## Gantt Chart w % Complete (hidden)
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6
Sprint 1
| Project Idea pitch | 2018-05-01 | 1 | 2018-05-19 | 19 | 19 | 0 | Gabriel | 100%
| Investigate the requirements | 2018-05-01 | 1 | 2018-05-19 | 19 | 15.2 | 3.8 | Robert | 80%
| Write a Project Plan | 2018-05-01 | 1 | 2018-05-19 | 19 | 11.4 | 7.6 | Robert | 60%
| Write a URS | 2018-05-01 | 1 | 2018-05-19 | 19 | 7.6 | 11.4 | Ibrahim | 40%
| Sprint 2 Goal | 2018-05-01 | 1 | 2018-05-19 | 19 | 3.8 | 15.2 | Gabriel | 20%
Sprint 2
| Develop user stories | 2018-05-20 | 20 | 2018-06-09 | 21 | 21 | 0 | Gabriel | 100%
| Write a Design Document | 2018-05-20 | 20 | 2018-06-09 | 21 | 16.8 | 4.2 | Robert | 80%
| Start building environment | 2018-05-20 | 20 | 2018-06-09 | 21 | 12.6 | 8.4 | Ibrahim | 60%
| Sprint 3 Goal | 2018-05-20 | 20 | 2018-06-09 | 21 | 8.4 | 12.6 | Ibrahim | 40%
Sprint 3
| Start Testing Client app | 2018-06-10 | 10 | 2018-06-29 | 20 | 20 | 0 | Robert | 100%
| Pen-testing and Security | 2018-06-10 | 10 | 2018-06-29 | 20 | 16 | 4 | Ibrahim | 80%
| Write a Manual | 2018-06-10 | 10 | 2018-06-29 | 20 | 12 | 8 | Gabriel | 60%
| Write Process Report | 2018-06-10 | 10 | 2018-06-29 | 20 | 8 | 12 | Robert | 40%
| Finalize URS & DD | 2018-06-10 | 10 | 2018-06-29 | 20 | 4 | 16 | Ibrahim | 20%
Sprint 4
| Deliver Project | 2018-07-01 | 1 | 2018-07-07 | 7 | 7 | 0 | Gabriel | 100%
| Assessment Week | 2018-07-01 | 1 | 2018-07-07 | 7 | 5.6 | 1.4 |  | 80%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Basic Gantt Chart (hidden)
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 4 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 4 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 6 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 7 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 4 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 8 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 3 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 5 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 5 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 4 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 10 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 6 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 7 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Manual Chart
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21
[5 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Sprint 1
| Project Idea pitch | 2020-09-07 | 2020-09-15 | 7 | bar: WEEK 2 M to WEEK 2 W; WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
| Investigate the requirements | 2020-09-07 | 2020-09-15 | 7 | bar: WEEK 2 M to WEEK 2 W; WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
| Write a Project Plan | 2020-09-16 | 2020-09-22 | 5 | bar: WEEK 3 M to WEEK 4 T; WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
| AWS Policy Conf. | 2020-09-14 | 2020-09-30 | 13 | bar: WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
| Write a URS | 2020-09-10 | 2020-10-02 | 17 | bar: WEEK 2 Th to WEEK 3 F; WEEK 4 Th to WEEK 5 F; WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
| Ansible setup | 2020-09-09 | 2020-10-04 | 18 | bar: WEEK 2 W to WEEK 3 F; WEEK 4 T to WEEK 5 F; WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
| Sprint Goal 2 | 2020-10-03 | 2020-10-04 | 0 | bar: WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
Sprint 2
| Develop user personas | 2020-09-14 | 2020-09-16 | 3 | bar: WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
Write a Design Document | bar: WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
| Playbooks configuration | 2020-09-15 | 2020-09-24 | 8 | bar: WEEK 4 T to WEEK 4 Th; WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
| Building the environment | 2020-09-11 | 2020-09-18 | 6 | bar: WEEK 2 Th to WEEK 3 F; WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
Sprint Goal 3 | bar: WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
Sprint 3
Creation of 2 VPCs and deployment of EC2 instances | bar: WEEK 4 F to WEEK 6 M; WEEK 7 T to WEEK 7 Th; WEEK 8 M; WEEK 8 W to WEEK 8 Th; WEEK 9 T to WEEK 10 M
Nat instance, TGW and ELB deployment | bar: WEEK 5 M to WEEK 6 T; WEEK 6 Th to WEEK 7 Th; WEEK 9 T to WEEK 9 F
Write a Manual | bar: WEEK 7 T to WEEK 8 Th; WEEK 9 M to WEEK 10 M
Sprint 4
Assessment Week | bar: WEEK 7 T to WEEK 7 Th; WEEK 9 T to WEEK 9 F
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])